## RFP Gap Tracker
AION — RFP gap tracker & task list
Proposal v3 mapped against RFP RTX-EOS-RFP-2026-0111 ¦ Every [MANDATORY] item tracked
# | RFP section | Requirement | What's in v3 today | Status | Priority | Owner | Due | Action needed
ARCHITECTURE DIAGRAMS (RFP 4.1) — 4 of 6 missing
1 | 4.1 Arch #1 | Current state (as-is) diagram | RFP includes one but proposal doesn't reference or reproduce it | MISSING | CRITICAL | Anish | Apr 11 | Build as-is architecture diagram showing 500+ apps, 10 system clusters, tech debt hotspots. Reference the RFP's own diagram.
2 | 4.1 Arch #3 | Integration architecture diagram | L6 table describes connectors but no standalone diagram | MISSING | CRITICAL | Anish | Apr 11 | Build diagram: SAP BTP + MuleSoft + Kafka + OPC-UA + MQTT + SIPR boundary. Show protocols, APIs, event patterns.
3 | 4.1 Arch #4 | Data architecture diagram | L3 describes lakehouse in text, no diagram | MISSING | CRITICAL | Anish | Apr 11 | Build end-to-end: OT tags -> AVEVA PI -> Databricks lakehouse -> AI Force -> apps. Show MDM, ITAR data mesh, batch vs real-time.
4 | 4.1 Arch #5 | Security architecture diagram | Section 5 has compliance matrix text, no diagram | MISSING | CRITICAL | Lenin | Apr 11 | Build zero-trust diagram: IT + OT zones, ITAR boundary, IAM (SailPoint), data classification (Varonis), CrowdStrike XDR, classified/unclassified split.
5 | 4.1 Arch #6 | Deployment architecture diagram | Not present | MISSING | HIGH | Anish | Apr 12 | Build hybrid deployment: Azure Gov + AWS GovCloud + on-prem DGX + edge (500+ sites). Show latency requirements (<10ms mfg vs batch analytics).
6 | 4.1 Arch #2 | Future state (to-be) diagram | Covered in text (Section 2.1) + SVG exists | PARTIAL | MEDIUM | Anish | Apr 12 | SVG exists. Convert to high-res PNG/PDF for K4K artifacts upload. Verify all 7 layers + 6 domains visible.
PILLAR 1: DELIVERY & GOVERNANCE — mostly missing detail
7 | P1 Governance | Steering committee composition + monthly cadence | Mentioned in passing at phase gates | PARTIAL | HIGH | Mark | Apr 12 | Add explicit paragraph: 'Monthly meeting chaired by RTX CEO/COO + HCL Engagement Partner + CFO + CTO. Board-level authority.'
8 | P1 Governance | RACI matrix | Not present | MISSING | HIGH | Mark | Apr 12 | Build RACI for key decisions: wave transitions, budget changes >5%, scope changes, vendor adds/removals. Include as appendix or table.
9 | P1 Governance | PMO cadence (weekly RAID, bi-weekly health, monthly financials) | Not detailed | MISSING | HIGH | Mark | Apr 12 | Add paragraph detailing: weekly RAID log, bi-weekly delivery health reports, monthly burn rate + forecast-at-completion + earned value tracking.
10 | P1 Governance | Real-time programme dashboard | Not present | MISSING | MEDIUM | Malika | Apr 13 | Describe 24/7 dashboard: workstream RAG status, budget burn, resource utilisation, risk register, value delivered to date. Reference L7 experience layer.
11 | P1 Governance | Outcome measurement with third-party auditor | Not present | MISSING | MEDIUM | Mark | Apr 13 | Add: 'Quarterly independent verification of outcome-based KPIs. Third-party auditor for financial outcomes.'
12 | P1 Governance | Model deployment gate checklist | Implicit in Tier 1 governance | PARTIAL | MEDIUM | Lenin | Apr 13 | Make explicit: every model entering production passes formal review of accuracy, bias testing, security validation, operational readiness, rollback plan, owner assignment.
13 | P1 Governance | Prime contractor + IP/data governance | Implicit | PARTIAL | MEDIUM | Mark | Apr 13 | Add explicit statement: HCL as single point of accountability. IP ownership per Section 10 terms. Role-based data access. All personnel background-checked.
PILLAR 2: WORKSHOPS — almost entirely missing
14 | P2 Workshops | Process mining across 6 domains | Referenced at headline in Phase 0 | PARTIAL | HIGH | Malika | Apr 12 | Expand Phase 0: describe process mining methodology, which 6 domains, output format. 'Document current-state workflows as they happen.'
15 | P2 Workshops | Design thinking sessions (business + tech together) | Not present | MISSING | HIGH | Malika | Apr 12 | Add new sub-section: design thinking sessions for each prioritised use case. Output = experience prototypes. Business users + technical teams co-facilitated.
16 | P2 Workshops | Joint architecture workshops with ADRs | Mentioned ('architecture ADRs') but no detail | PARTIAL | MEDIUM | Anish | Apr 13 | Expand: technical deep dives with RTX enterprise architecture, OT, and security teams. Output = jointly authored Architecture Decision Records.
17 | P2 Workshops | OT integration sessions with DCS engineers | Not present | MISSING | MEDIUM | Anish | Apr 13 | Add: dedicated workshops with DCS engineers, process control admins, plant instrumentation teams.
18 | P2 Workshops | Quarterly board-level strategic sessions | Not present | MISSING | MEDIUM | Mark | Apr 13 | Add: quarterly executive alignment sessions with RTX C-suite. Strategic conversations about competitive positioning + next-wave investment decisions.
19 | P2 Workshops | Train-the-trainer programme | Not present | MISSING | HIGH | Malika | Apr 12 | Add new sub-section in CoE: formal programme to train RTX CoE team to independently facilitate workshops, design use cases, build models, deploy to production.
20 | P2 Workshops | 50 certified AI practitioners by Month 30 | Not present | MISSING | HIGH | Malika | Apr 12 | Add specific target: internal AI practitioner certification for RTX employees. Minimum 50 certified by Month 30.
PILLAR 3: CoE — headlines covered, detail missing
21 | P3 CoE | AI playbook published by Month 12 | Not explicitly mentioned | MISSING | HIGH | Malika | Apr 12 | Add: 'By Month 12, publish RTX's internal AI Playbook: how AI projects are initiated, developed, tested, deployed, monitored, and retired.'
22 | P3 CoE | 10 independent use cases by Month 24 | Not present | MISSING | HIGH | Malika | Apr 12 | Add to Phase 2 exit criteria: 'CoE must have independently delivered at least 10 AI use cases into production without HCL-led development.'
23 | P3 CoE | Staffing target: 15-20 internal CoE resources by Phase 3 | Not present | MISSING | MEDIUM | Malika | Apr 13 | Add: minimum 15-20 internal CoE resources by Month 25: AI/ML engineers, data engineers, product manager, change manager, AI ethics officer. All certified.
24 | P3 CoE | CoE as AI governance body in Phase 3 | Mentioned at headline | PARTIAL | MEDIUM | Lenin | Apr 13 | Expand: CoE approving models for production, monitoring bias/drift, managing model registry, enforcing ethical AI standards.
PILLAR 4: ADVISORY — mostly missing
25 | P4 Advisory | AI-enabled operating model blueprint by Month 6 | Not present | MISSING | HIGH | Mark | Apr 12 | Add: 'Deliver AI-Enabled Operating Model Blueprint by Month 6, updated quarterly. Which decisions become AI-augmented, which roles evolve, which new roles emerge.'
26 | P4 Advisory | 5-year technology futures report (annually updated) | Not present | MISSING | MEDIUM | Mark | Apr 13 | Add: annually updated Technology Futures Report specific to aerospace/defense. Include emerging tech scouting.
27 | P4 Advisory | Role evolution + skills gap analysis | Not present | MISSING | HIGH | Malika | Apr 12 | Add: role elevation advisory co-designed with HR. Map current workforce capabilities against AI-enabled operating model requirements.
28 | P4 Advisory | Tech debt reduction roadmap with business case per app | Mentioned (500->180 target) but no methodology | PARTIAL | HIGH | Anish | Apr 12 | Expand: structured plan with business case for each rationalisation decision. Not just a target number.
29 | P4 Advisory | Board readiness / executive education | Not present | MISSING | MEDIUM | Mark | Apr 13 | Add: prepare RTX board for AI governance decisions. Board briefing materials, risk frameworks in board-ready language.
PILLAR 5: ETHICS & COMPLIANCE — well covered, minor gaps
30 | P5 Ethics | Responsible AI policy within first 90 days | Section 5 covers Tier framework but doesn't specify 90-day delivery | PARTIAL | HIGH | Lenin | Apr 12 | Add explicit: 'Comprehensive Responsible AI framework established within first 90 days covering fairness, transparency, accountability, privacy, safety. Co-designed with RTX legal + compliance + HSE.'
31 | P5 Ethics | Bias monitoring (continuous, quarterly fairness audits) | Mentioned in AI Force GRC description | PARTIAL | MEDIUM | Lenin | Apr 13 | Make explicit: continuous bias monitoring for all HR, procurement, and commercial AI models. Quarterly fairness audits.
32 | P5 Ethics | AI incident response plan | Not present | MISSING | HIGH | Lenin | Apr 12 | Add: documented procedure for AI errors. Severity levels, escalation paths, model rollback, root cause analysis.
33 | P5 Ethics | Human override logged for model improvement | Mentioned as 'hard-coded' override | PARTIAL | LOW | Lenin | Apr 13 | Clarify: override patterns are logged and fed back into model improvement. Not just kill-switch but learning loop.
PILLAR 6: CHANGE MANAGEMENT — not in the proposal at all
34 | P6 Change | Workforce impact assessment (who affected, how workflow changes, skills needed) | Not present | MISSING | CRITICAL | Malika | Apr 11 | NEW SECTION NEEDED. Before any AI deploys, document per use case: who affected, workflow changes, skills needed. 185K employees + 60K contractors.
35 | P6 Change | Stakeholder mapping (Champions, Pragmatists, Skeptics, Resistors) | Not present | MISSING | CRITICAL | Malika | Apr 11 | Add stakeholder segmentation with different engagement strategy per segment.
36 | P6 Change | Operator co-design programme | Not present | MISSING | CRITICAL | Malika | Apr 11 | Add: change programme designed WITH operators, not imposed on them. They are the most important and most sceptical users.
37 | P6 Change | 80%+ adoption target within 6 months of each deployment | Not present | MISSING | HIGH | Malika | Apr 12 | Add measurable adoption target: 80%+ of targeted users actively using AI tools within 6 months. Measured by decision quality metrics, not login counts.
38 | P6 Change | Multi-channel comms (CEO town halls, floor sessions, AI Stories) | Not present | MISSING | HIGH | Malika | Apr 12 | Add: communication strategy from Day 1 through Month 36. CEO town halls, floor-level sessions, digital channels, 'AI Stories' case studies.
39 | P6 Change | Three-level training programme (L1 all staff, L2 users, L3 builders) | Not present | MISSING | CRITICAL | Malika | Apr 11 | Add: L1 AI Awareness (all 245K), L2 AI User (primary users), L3 AI Builder (CoE + power users, 50-100 people, multi-week certification). Continuous, not one-time.
40 | P6 Change | Adoption metrics beyond login counts | Not present | MISSING | HIGH | Malika | Apr 12 | Add: measure decision quality improvement, time savings, user satisfaction (NPS), override rates.
RFP SECTION 5: PLATFORM, RISK & AGENTIC — gaps
41 | 5.4 Risk | 25 identified risks with mitigations | Not present | MISSING | HIGH | Lenin | Apr 12 | Build risk register: minimum 25 risks with mitigation strategies and residual risk ratings. Cover tech, delivery, compliance, change, commercial risks.
42 | 5.5 Agentic | Agentic AI strategy with autonomous decision boundaries | Section 2.2 covers agents but no explicit 'strategy' framing | PARTIAL | MEDIUM | Anish | Apr 13 | Reframe Section 2.2 intro as an 'Agentic AI Strategy': multi-agent orchestration, autonomous decision boundaries, human-in-loop governance. Currently reads as a feature list.
43 | 5.2 Integration | Non-SAP integration strategy per system | Section 2.1 L6 lists systems but doesn't say 'integrate or rationalise' per system | PARTIAL | MEDIUM | Anish | Apr 13 | Add explicit disposition per non-SAP system: Teamcenter (integrate), Windchill (integrate), Salesforce (integrate), Workday (integrate), ServiceNow (integrate), SIPR (boundary adapter), 500+ apps (rationalise).
RFP SECTION 6: COMMERCIAL — minor gaps
44 | 6.2 ROI | NPV analysis with discount rates and stated assumptions | Section 6.3 has scenario analysis but no NPV | MISSING | HIGH | Mark | Apr 12 | Add NPV calculation with explicit discount rate (e.g. 10% WACC), stated assumptions. Currently only has payback + scenario table.
45 | 6.2 ROI | Sensitivity analysis (pessimistic 60%, baseline 100%, optimistic 140%) | Present in Section 6.3 | COVERED | LOW | — | — | Already done.
46 | 6.2 ROI | Revenue growth path (new revenue streams, quality premiums) | Not present — only cost savings | MISSING | MEDIUM | Mark | Apr 13 | Add: how AI capabilities create new revenue (Readiness-as-a-Service, aftermarket pricing optimisation, defense win rate improvement). Currently only shows cost avoidance.
CONTENT QUALITY — cross-cutting
47 | Cross-cutting | Supplier count: proposal says 14,000, RFP says 40,000 | Inconsistent with RFP | PARTIAL | CRITICAL | Malika | Apr 11 | Find-and-replace all '14,000' to '40,000' throughout proposal. The RFP explicitly says 40,000+ suppliers.
48 | Cross-cutting | Humanise the document — reads too technical/AI-generated | Team feedback from all-hands call | PARTIAL | CRITICAL | Malika + PreSales | Apr 12 | Run humaniser pass on all sections. Best done in Claude Code: docx -> md -> humaniser per section -> rebuild docx.
49 | Cross-cutting | Proposal currently 27 pages — max is 50 pages | Room to add missing pillars | INFO | MEDIUM | Malika | Apr 13 | 23 pages of headroom. Use it for: Change Management section (~3 pages), Workshop detail (~2 pages), Advisory section (~2 pages), Risk register (~2 pages), RACI (~1 page).
50 | Cross-cutting | K4K platform — upload all artifacts | Need to verify all 8 submission slots populated | PARTIAL | HIGH | All | Apr 13 | Check: TP, CP, Costing, Team Profiles, Artifacts (6 arch diagrams + 3 case studies), Demo Video, RFP Response, NDA.
SUMMARY
| MISSING | 22 | Items not addressed at all in v3 — need writing from scratch
| PARTIAL | 14 | Items partially covered — need expanding or making explicit
| COVERED | 2 | Items fully addressed
| CRITICAL | 8 | Items that must be done by Apr 11 — blocking submission quality
| HIGH | 20 | Items due Apr 12 — core proposal completeness
| MEDIUM | 15 | Items due Apr 13 — polish and differentiation