## Risk Register
# | Risk | Category | Likelihood | Impact | Mitigation | Residual Risk | Owner | Phase
1 | SAP ECC end-of-support Dec 2027 | Technical | Medium | High | Base90 compresses S/4 build by 8-12 months; HANASmart automates ABAP migration | Low | HCL SAP Lead | P1
2 | ITAR data egress during AI model training | Compliance | Low | Critical | AI Force on-prem deployment, zero cloud egress for classified, Butler cleared facilities | Low | Lenin (Compliance) | P0
3 | GTF inspection backlog worsens during transformation | Operational | Medium | High | iMRO/4 deployed in parallel, no dependency on EOS platform completion | Medium | HCL Delivery | P1
4 | Operator resistance to AI-augmented processes | Change | High | High | Operator co-design programme, reverse mentoring, 80%+ adoption target measured quarterly | Medium | Malika (Change) | P0-P3
5 | Model drift in safety-critical manufacturing AI | AI Risk | Medium | Critical | 90-day mandatory revalidation, continuous drift monitoring, hard human override on all Tier 1 | Low | HCL AI Lead | P1-P3
6 | CMMC Level 2/3 certification delay | Compliance | Low | High | CrowdStrike + Palo Alto deployed Phase 1; 3+ months buffer before Nov 2026 deadline | Low | Lenin (Compliance) | P1
7 | Budget overrun on phased delivery | Commercial | Medium | Medium | Fixed price per phase with milestone gates; no payment without Steering Committee sign-off | Low | Mark (Commercial) | P0-P3
8 | Classified/unclassified boundary breach | Security | Low | Critical | AI Force GRC enforces boundary at architecture level; SailPoint US-person-only access | Low | Lenin (Compliance) | P0
9 | Key personnel turnover (HCL side) | Delivery | Medium | Medium | Named backups for all critical roles; RTX co-secondees provide continuity | Low | HCL Program Dir | P0-P3
10 | Integration failure with legacy OT systems | Technical | Medium | High | Dedicated OT workshops Phase 0; proven Siemens/AVEVA/Rockwell connectors | Medium | Anish (Solution) | P0-P1
11 | AI hallucination in defence contract pricing | AI Risk | Medium | High | Tier 2 governance with Program Director approval; all outputs auditable | Low | HCL AI Lead | P2
12 | Supply chain disruption during transformation | Operational | High | Medium | Guardian Supplier Risk Engine deployed as Quick Win (Month 2-3) | Medium | HCL Delivery | P0
13 | Rare material (Ti/Co/Re) sourcing bottleneck | Strategic | Medium | High | iSCM geopolitical risk scoring + alternative sourcing intelligence | Medium | HCL Supply Chain | P2
14 | Insufficient RTX CoE staffing by Month 24 | Capability | Medium | High | 15-20 CoE resource target contractually defined; HCL trains and certifies | Low | Malika (Change) | P2
15 | SOX compliance gap during financial close automation | Compliance | Low | High | SOX-compatible audit trail from Day 1; CFO dashboard with immutable decision trail | Low | Lenin (Compliance) | P1
16 | Nation-state cyber attack on defence IP | Security | Medium | Critical | CrowdStrike Falcon XDR + Palo Alto Cortex; zero-trust architecture | Medium | Lenin (Compliance) | P0-P3
17 | Scope creep from RTX business units | Delivery | High | Medium | Steering Committee approval for scope changes >5%; documented RACI | Low | Mark (Commercial) | P0-P3
18 | Data quality issues in legacy systems | Technical | High | Medium | Phase 0 data audit; MDM governance established before AI deployment | Medium | Anish (Solution) | P0
19 | Competing priorities across 3 RTX segments | Organisational | High | Medium | Segment-specific delivery leads; unified Steering Committee governance | Medium | HCL Program Dir | P0-P3
20 | NDAA Section 1513 compliance deadline (June 2026) | Compliance | Low | High | AI Force GRC provides framework; Phase 1 deployment ahead of deadline | Low | Lenin (Compliance) | P1
21 | Digital twin latency in manufacturing environments | Technical | Medium | Medium | Dell EMC edge compute with sub-10ms latency; NVIDIA DGX on-prem | Low | Anish (Solution) | P2
22 | Vendor lock-in concerns from RTX procurement | Commercial | Medium | Medium | All licences held by RTX; annual review with full switch rights; no lock-in architecture | Low | Mark (Commercial) | P0-P3
23 | Security clearance bottleneck for HCL personnel | Delivery | Medium | High | Butler Aerospace pre-cleared facilities; 7 ITAR-compliant US centres | Low | HCL Program Dir | P0
24 | AI bias in HR and procurement models | Ethics | Medium | High | Continuous bias monitoring; quarterly fairness audits; DataRobot explainability | Low | Lenin (Compliance) | P1-P3
25 | Post-merger cultural resistance between legacy companies | Change | High | Medium | Segment-specific engagement; Champions/Pragmatists/Skeptics/Resistors mapping | Medium | Malika (Change) | P0-P3